## Task Tracker
WBS | Task | Description | Predecessors | Duration | Start Date | End Date | Role | Assigned To | % Allocation | Status | % Complete | Health | At Risk | WBS Helper Columns-> | Skip WBS | WBS Phase | Row ID | Row | Parent Row | Level | Ancestors | Children
| Project Superstore Sales Performance Dashboard |  |  | 28d | 2025-07-08 | 2025-08-04 |  |  |  | In Progress |  | Green |  |  | TRUE |  | 12 | 1 |  |  | 0 | 6
1 | Planning & Setup | This phase establishes the foundational elements of the project, including defining scope, setting up the environment, and identifying key analytical questions. |  | 5d | 2025-07-08 | 2025-07-12 | BA Dev PM | Lashawn Fofung | 100% |  |  | Green |  |  |  | 1 - Planning & Setup | 13 | 2 | 12 | 1 | 1 | 6
1.1 | Define project scope & requirement | Formalize project boundaries, deliverables, and success criteria. |  | 2d | 2025-07-08 | 2025-07-09 | BA Dev PM | Lashawn Fofung | 100% |  |  | Yellow |  |  |  | 1 - Planning & Setup | 14 | 3 | 13 | 1 | 2 | 0
1.2 | Set up project GitHub repository and README | Create the GitHub repository for the project, initialize it, and draft the initial content for the README.md file, including the project description and basic setup instructions. |  | 1d | 2025-07-08 | 2025-07-08 | BA Dev | Lashawn Fofung | 100% |  |  | Red |  |  |  | 1 - Planning & Setup | 46 | 4 | 13 | 2 | 2 | 0
1.3 | Set up Project Workspace in Smartsheet | Create and configure the project workspace in Smartsheet, including WBS, Dashboard, and resource(s). | 3 | 2d | 2025-07-10 | 2025-07-11 | BA Dev | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 1 - Planning & Setup | 25 | 5 | 13 | 3 | 2 | 0
1.4 | Obtain/Verify data source | Locate and confirm accessibility and integrity of the source data file. | 3 | 1d | 2025-07-10 | 2025-07-10 | BA Dev PM | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 1 - Planning & Setup | 15 | 6 | 13 | 4 | 2 | 0
1.5 | Set up Tableau environment | Install or configure Tableau Desktop/Public, ensuring it's ready for development. | 3 | 1d | 2025-07-10 | 2025-07-10 | BA Dev | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 1 - Planning & Setup | 24 | 7 | 13 | 5 | 2 | 0
1.6 | Develop Insightful Questions | Brainstorm and finalize key business questions to be answered by the dashboard. | 7 | 2d | 2025-07-11 | 2025-07-12 | BA Dev | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 1 - Planning & Setup | 23 | 8 | 13 | 6 | 2 | 0
2 | Data Preparation | This phase focuses on acquiring, connecting to, and performing initial validation of the project's data source. | 5 | 1d | 2025-07-13 | 2025-07-13 | BA Dev PM | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 2 - Data Preparation | 16 | 9 | 12 | 2 | 1 | 2
2.1 | Connect to data & create extract | Establish data connection in Tableau and create an optimized data extract. | 2 | 1d | 2025-07-13 | 2025-07-13 | BA Dev | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 2 - Data Preparation | 17 | 10 | 16 | 1 | 2 | 0
2.2 | Basic data validation | Perform initial checks on data quality and consistency. | 2 | 1d | 2025-07-13 | 2025-07-13 | BA Dev | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 2 - Data Preparation | 18 | 11 | 16 | 2 | 2 | 0
3 | Visualization Development | This phase involves the creation of all individual charts and views required for the dashboard. | 9 | 7d | 2025-07-14 | 2025-07-20 | BA Dev PM | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 3 - Visualization Development | 20 | 12 | 12 | 3 | 1 | 5
3.1 | Create KPI Scorecards (4 views) | Develop individual sheets for Total Sales, Total Profit, Total Volume, and Sales Per Customer. | 11 | 3d | 2025-07-14 | 2025-07-16 | BA Dev | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 3 - Visualization Development | 29 | 13 | 20 | 1 | 2 | 0
3.2 | Create Sales by Region (Pie Chart) | Build the visualization showing sales distribution across regions. | 13 | 1d | 2025-07-17 | 2025-07-17 | BA Dev | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 3 - Visualization Development | 30 | 14 | 20 | 2 | 2 | 0
3.3 | Create Top N States (Bar Chart) | Develop the dynamic bar chart for top-performing states by sales. | 14 | 1d | 2025-07-18 | 2025-07-18 | BA Dev | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 3 - Visualization Development | 31 | 15 | 20 | 3 | 2 | 0
3.4 | Create Sales by Sub-Category (Bubbles Chart) | Construct the bubble chart to visualize sales per sub-category. | 15 | 1d | 2025-07-19 | 2025-07-19 | BA Dev | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 3 - Visualization Development | 21 | 16 | 20 | 4 | 2 | 0
3.5 | Create Sales Trend (Line Chart) | Develop the line chart to show sales performance over time. | 16 | 1d | 2025-07-20 | 2025-07-20 | BA Dev | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 3 - Visualization Development | 22 | 17 | 20 | 5 | 2 | 0
4 | Dashboard Assembly | This phase focuses on integrating all developed visualizations into a cohesive and interactive Tableau dashboard, including layout, filtering, and final formatting. | 17 | 5d | 2025-07-21 | 2025-07-25 | BA Dev PM | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 4 - Dashboard Assembly | 26 | 18 | 12 | 4 | 1 | 6
4.1 | Design Dashboard Layout & Containers | Plan and implement the structural arrangement of visualizations using containers. | 16 | 1d | 2025-07-21 | 2025-07-21 | BA Dev QA | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 4 - Dashboard Assembly | 32 | 19 | 26 | 1 | 2 | 0
4.2 | Integrate all worksheets into dashboard | Add all developed individual sheets onto the main dashboard canvas. | 19 | 1d | 2025-07-22 | 2025-07-22 | BA Dev QA | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 4 - Dashboard Assembly | 33 | 20 | 26 | 2 | 2 | 0
4.3 | Implement Filters(Order Date, Segment) | Add and configure interactive filters for dashboard control. | 20 | 1d | 2025-07-23 | 2025-07-23 | BA Dev QA | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 4 - Dashboard Assembly | 34 | 21 | 26 | 3 | 2 | 0
4.4 | Implement Action Filters (Pie & Bubble Charts) | Set up dashboard actions to enable drill-down functionality from key charts. | 21 | 1d | 2025-07-24 | 2025-07-24 | BA Dev QA | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 4 - Dashboard Assembly | 35 | 22 | 26 | 4 | 2 | 0
4.5 | Fine-tune formatting, legends, titles | Adjust colors, fonts, legends, and titles for consistency and visual appeal. | 22 | 1d | 2025-07-25 | 2025-07-25 | BA Dev QA | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 4 - Dashboard Assembly | 39 | 23 | 26 | 5 | 2 | 0
4.6 | Hide sheets, final clean-up | Conceal all individual worksheets and perform final workbook optimization. | 22 | 1d | 2025-07-25 | 2025-07-25 | BA Dev QA | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 4 - Dashboard Assembly | 40 | 24 | 26 | 6 | 2 | 0
5 | Documentation | This phase is dedicated to producing all required project documentation, such as the case study, GitHub repository description, and illustrative SQL queries. | 24 | 6d | 2025-07-26 | 2025-07-31 | BA PM | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 5 - Documentation | 27 | 25 | 12 | 5 | 1 | 3
5.1 | Write Case Study | Draft comprehensive project case study outlining analysis, insights, and recommendations. | 24 | 3d | 2025-07-26 | 2025-07-28 | BA PM | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 5 - Documentation | 36 | 26 | 27 | 1 | 2 | 0
5.2 | Write Tableau Story Summary | Create a brief narrative summary for Tableau Story. | 26 | 1d | 2025-07-29 | 2025-07-29 | BA PM | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 5 - Documentation | 38 | 27 | 27 | 2 | 2 | 0
5.3 | Formulate SQL Queries | Develop illustrative SQL queries for use cases and case studies. | 27 | 2d | 2025-07-30 | 2025-07-31 | BA PM | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 5 - Documentation | 37 | 28 | 27 | 3 | 2 | 0
6 | Review & Closeout | This phase involves internal testing, addressing feedback, and formalizing the project's completion and submission. | 28 | 4d | 2025-08-01 | 2025-08-04 | BA Dev PM QA | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 6 - Review & Closeout | 28 | 29 | 12 | 6 | 1 | 5
6.1 | Internal review & testing | Conduct thorough testing of dashboard functionality and data accuracy. | 28 | 1d | 2025-08-01 | 2025-08-01 | BA Dev QA | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 6 - Review & Closeout | 42 | 30 | 28 | 1 | 2 | 0
6.2 | Address feedback & revisions | Incorporate feedback from reviews and make necessary adjustments. | 30 | 1d | 2025-08-02 | 2025-08-02 | BA Dev QA | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 6 - Review & Closeout | 43 | 31 | 28 | 2 | 2 | 0
6.3 | Publish to Tableau Public | Publish the final Tableau workbook to Tableau Public. | 31 | 1d | 2025-08-03 | 2025-08-03 | BA Dev QA | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 6 - Review & Closeout | 44 | 32 | 28 | 3 | 2 | 0
6.4 | Update Github Repo Description | Update the README content for project's GitHub repository. | 31 | 1d | 2025-08-03 | 2025-08-03 | BA Dev PM | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 6 - Review & Closeout | 45 | 33 | 28 | 4 | 2 | 0
6.5 | Final project submission | Submit all project deliverables as per requirements. | 32, 33 | 1d | 2025-08-04 | 2025-08-04 | BA Dev PM | Lashawn Fofung | 100% |  |  | Gray |  |  |  | 6 - Review & Closeout | 41 | 34 | 28 | 5 | 2 | 0

## Summary
Current Phase | #INVALID COLUMN VALUE
Project Health | Green
Project Status | In Progress
Tasks at Risk | TRUE