## Task Tracker_WBS
WBS Level | Task | Description | Predecessors | Duration | Start Date | End Date | Role | Assigned To | % Allocation | Status | % Complete | Health | At Risk | Skip WBS | Deliverables | Acceptance Criteria | Risk/Assumptions | WBS Phase | Row | Parent Row | Row ID | Level | Ancestors | Children
| Project Superstore Sales Performance Dashboard |  |  | 35d | 2025-07-08 | 2025-08-11 |  |  |  | In Progress | 31% | Green |  | TRUE |  |  |  |  | 1 |  | 134 |  | 0 | 6
1 | Planning & Setup | This phase establishes the foundational elements of the project, including defining scope, setting up the environment, and identifying key analytical questions. |  | 9d | 2025-07-08 | 2025-07-16 | BA Dev PM | Lashawn Fofung | 100% | In Progress | 100% | Green | [5 empty] | 1-Planning & Setup | 2 | 134 | 135 | 1 | 1 | 7
1.1 | Define project scope & requirement | Formalize project boundaries, deliverables, and success criteria. |  | 2d | 2025-07-08 | 2025-07-09 | BA Dev PM | Lashawn Fofung | 100% | Complete | 100% | Green |  |  | Project Scope Document, Requirements List | Scope document signed off by sponsor; Requirements list is comprehensive and unabmbiguous. | Risk: Misinterpretation of requirements. | 1-Planning & Setup | 3 | 135 | 136 | 1 | 2 | 0
1.2 | Set up project GitHub repository and description | Create the GitHub repository for the project, initialize it, and draft the initial content for the README.md file, including the project description and basic setup instructions. | 3 | 1d | 2025-07-10 | 2025-07-10 | BA Dev | Lashawn Fofung | 100% | Complete | 100% | Green |  |  | Draft README.md file content | Description is concise and accurate. |  | 1-Planning & Setup | 4 | 135 | 137 | 2 | 2 | 0
1.3 | Create project schedule and timeline | Create and configure the project's schedule, timeline, and Kanban board in Smartsheet. | 4 | 2d | 2025-07-11 | 2025-07-12 | BA Dev | Lashawn Fofung | 100% | Complete | 100% | Green |  |  | Finalized project schedule and timeline | Project schedule and timeline complete. |  | 1-Planning & Setup | 5 | 135 | 138 | 3 | 2 | 0
1.4 | Obtain/Verify data source | Locate and confirm accessibility and integrity of the source data file. | 5 | 1d | 2025-07-13 | 2025-07-13 | BA Dev PM | Lashawn Fofung | 100% | Complete | 100% | Green | [5 empty] | 1-Planning & Setup | 6 | 135 | 139 | 4 | 2 | 0
1.5 | Set up Tableau environment | Install or configure Tableau Desktop/Public, ensuring it's ready for development. | 6 | 1d | 2025-07-14 | 2025-07-14 | BA Dev | Lashawn Fofung | 100% | Complete | 100% | Green |  |  | Configured Tableau Deskto/Public | Tableau software is installed, licensed, and functional. | Risk: Tableau technical challenges | 1-Planning & Setup | 7 | 135 | 140 | 5 | 2 | 0
1.6 | Develop Insightful Questions | Brainstorm and finalize key business questions to be answered by the dashboard. | 7 | 2d | 2025-07-15 | 2025-07-16 | BA Dev | Lashawn Fofung | 100% | Complete | 100% | Gray |  |  | Finalized Insightful Questions | Questions are reviewed, approved by stakeholders, and align with business objectives. | Assumptions: Users have basic data literacy; Questions guide analysis. | 1-Planning & Setup | 8 | 135 | 141 | 6 | 2 | 0
1.7 | Project Planning & Setup Complete Milestone | All initial project definitions, scope, requirements, data source verification, and environment setup are finalized. Insightful questions are developed. | 8 | 0 | 2025-07-16 | 2025-07-16 | PM | Lashawn Fofung | 100% | Complete | 100% | Gray |  |  | Project Scope Document, Requirements List, Insightful Questions List, Configured Tableau Environment | All project definitions and requirements are finalized and approved by stakeholders; Development environment is ready; Key analytical questions are defined. | Risks: Misinterpretation of requirements. Assumptions: Fictitious company context helps clarify objectives. | 1-Planning & Setup | 9 | 135 | 142 | 7 | 2 | 0
2 | Data Preparation | This phase focuses on acquiring, connecting to, and performing initial validation of the project's data source. | 8 | 2d | 2025-07-17 | 2025-07-18 | BA Dev PM | Lashawn Fofung | 100% | Not Started | 100% | Gray | [5 empty] | 2-Data Preparation | 10 | 134 | 143 | 2 | 1 | 3
2.1 | Connect to data & create extract | Establish data connection in Tableau and create an optimized data extract. | 9 | 1d | 2025-07-17 | 2025-07-17 | BA Dev | Lashawn Fofung | 100% | Complete | 100% | Gray |  |  | Tableau Data Extract | Data connection established; Extract created successfully. | Assumption: Data source accuracy | 2-Data Preparation | 11 | 143 | 144 | 1 | 2 | 0
2.2 | Basic data validation | Perform initial checks on data quality and consistency. | 11 | 1d | 2025-07-18 | 2025-07-18 | BA Dev | Lashawn Fofung | 100% | Complete | 100% | Gray |  |  | Data Validation Report/Log | Key fields are checked for completeness, format, and range; No critical data integrity issues found. | Risk: Data inconsistencies/error | 2-Data Preparation | 12 | 143 | 145 | 2 | 2 | 0
2.3 | Data Preparation Complete Milestone | The Superstore.xls data is connected in Tableau, extracted, and basic data validation is performed, making it ready for visualization development. | 12 | 0 | 2025-07-18 | 2025-07-18 | PM | Lashawn Fofung | 100% | Complete | 100% | Gray |  |  | Tableau Data Extract | Data extract is created successfully from Superstore.xls and basic data validation shows no critical issues; Data is confirmed ready for visualization. | Risks: Data inconsistencies/errors. Assumptions: Data source is stable and initially clean. | 2-Data Preparation | 13 | 143 | 146 | 3 | 2 | 0
3 | Visualization Development | This phase involves the creation of all individual charts and views required for the dashboard. | 8 | 7d | 2025-07-19 | 2025-07-25 | BA Dev PM | Lashawn Fofung | 100% | Not Started | 0% | Gray | [5 empty] | 3-Visualization Development | 14 | 134 | 147 | 3 | 1 | 6
3.1 | Create KPI Scorecards (4 views) | Develop individual sheets for Total Sales, Total Profit, Total Volume, and Sales Per Customer. | 13 | 3d | 2025-07-19 | 2025-07-21 | BA Dev | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Tableau Worksheet Files (KPIs) | Each KPI view displays the correct metric (Sales, Profit, Volume, Sales/Customer) with specified formatting. | Risk: Formatting difficulties | 3-Visualization Development | 15 | 147 | 148 | 1 | 2 | 0
3.2 | Create Sales by Region (Pie Chart) | Build the visualization showing sales distribution across regions. | 15 | 1d | 2025-07-22 | 2025-07-22 | BA Dev | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Tableau Worksheet File (Pie Chart) | Pie chart accurately represents regional sales; Formatting (colors, labels) meeting requirements. | Risk: Formatting difficulties | 3-Visualization Development | 16 | 147 | 149 | 2 | 2 | 0
3.3 | Create Top N States (Bar Chart) | Develop the dynamic bar chart for top-performing states by sales. | 16 | 1d | 2025-07-23 | 2025-07-23 | BA Dev | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Tableau Worksheet File (Bar Chart) | Bar chart correctly displays top N states; N parameter functions; Formatting meets requirements. | Risk: Formatting difficulties | 3-Visualization Development | 17 | 147 | 150 | 3 | 2 | 0
3.4 | Create Sales by Sub-Category (Bubbles Chart) | Construct the bubble chart to visualize sales per sub-category. | 17 | 1d | 2025-07-24 | 2025-07-24 | BA Dev | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Tableau Worksheet File (Bubble chart) | Bubble chart accurately displays sales by sub-category; Color by category works; Formatting meets requirements. | Risks: Formatting difficulties | 3-Visualization Development | 18 | 147 | 151 | 4 | 2 | 0
3.5 | Create Sales Trend (Line Chart) | Develop the line chart to show sales performance over time. | 18 | 1d | 2025-07-25 | 2025-07-25 | BA Dev | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Tableau Worksheet File (Line Chart) | Line chart accurately show sales trend over time (Month-Year); Formatting meets requirements. | Risk: Formatting difficulties | 3-Visualization Development | 19 | 147 | 152 | 5 | 2 | 0
3.6 | Core Visualizations Developed Milestone | All individual charts and KPI scorecards are created and ready for integration into the dashboard. | 19 | 0 | 2025-07-25 | 2025-07-25 | PM | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | All individual Tableau Worksheet Files (KPIs, Charts) | All required KPI scorecards and chart types (Pie, Bar, Bubble, Line) are created, display accurate data, and meet preliminary formatting standards. | Risks: Tableau technical challenges; Formatting difficulties. Assumptions: Tableau environment is functional. | 3-Visualization Development | 20 | 147 | 153 | 6 | 2 | 0
4 | Dashboard Assembly | This phase focuses on integrating all developed visualizations into a cohesive and interactive Tableau dashboard, including layout, filtering, and final formatting. | 20 | 6d | 2025-07-26 | 2025-07-31 | BA Dev PM | Lashawn Fofung | 100% | Not Started | 0% | Gray | [5 empty] | 4-Dashboard Assembly | 21 | 134 | 154 | 4 | 1 | 7
4.1 | Design Dashboard Layout & Containers | Plan and implement the structural arrangement of visualizations using containers. | 20 | 1d | 2025-07-26 | 2025-07-26 | BA Dev QA | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Dashboard Layout Plan (internal), Draft Dashboard | Dashboard layout adheres to specified fixed size (1055x850); Containers are correctly structured. | Risk: Formating difficulties | 4-Dashboard Assembly | 22 | 154 | 155 | 1 | 2 | 0
4.2 | Integrate all worksheets into dashboard | Add all developed individual sheets onto the main dashboard canvas. | 22 | 1d | 2025-07-27 | 2025-07-27 | BA Dev QA | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Assembled Tableau Dashboard (draft) | All 9 developed worksheets are correctly placed and visible within the dashboard. | Risk: Formatting difficulties | 4-Dashboard Assembly | 23 | 154 | 156 | 2 | 2 | 0
4.3 | Implement Filters(Order Date, Segment) | Add and configure interactive filters for dashboard control. | 23 | 1d | 2025-07-28 | 2025-07-28 | BA Dev QA | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Functional Dashboard Filters | All specified filters are present, linked to relevant views, and function correctly with " Apply" buttons. | Risk: Tableau technical challenges | 4-Dashboard Assembly | 24 | 154 | 157 | 3 | 2 | 0
4.4 | Implement Action Filters (Pie & Bubble Charts) | Set up dashboard actions to enable drill-down functionality from key charts. | 24 | 1d | 2025-07-29 | 2025-07-29 | BA Dev QA | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Functional Dashboard Actions | Pie chart and Bubble chart actions filter the rest of the dashboard accurately upon click. | Risk: Tableau technical challenges | 4-Dashboard Assembly | 25 | 154 | 158 | 4 | 2 | 0
4.5 | Fine-tune formatting, legends, titles | Adjust colors, fonts, legends, and titles for consistency and visual appeal. | 25 | 1d | 2025-07-30 | 2025-07-30 | BA Dev QA | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Formatted Dashboard | All visual elements (legends, titles, borders, colors) comply with project formatting guidelines. | Risk: Formatting difficulties | 4-Dashboard Assembly | 26 | 154 | 159 | 5 | 2 | 0
4.6 | Hide sheets, final clean-up | Conceal all individual worksheets and perform final workbook optimization. | 26 | 1d | 2025-07-31 | 2025-07-31 | BA Dev QA | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Cleaned Tableau Workbook | All individual worksheets are hidden; Workbook is optimized for publishing (e.g., unused fields hidden) |  | 4-Dashboard Assembly | 27 | 154 | 160 | 6 | 2 | 0
4.7 | Dashboard Assembly Complete Milestone | The interactive Tableau dashboard is fully assembled, including layout design, integration of all worksheets, implementation of filters and actions, and final formatting. All sheets are hidden. | 27 | 0 | 2025-07-31 | 2025-07-31 | PM | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Fully assembled and formatted Tableau Dashboard (superstore_sales_performance.twbx) | The dashboard adheres to specified layout, fixed size, includes all integrated worksheets, and features fully functional filters and actions; All individual sheets are hidden. | Risks: Tableau technical challenges; Formatting difficulties. | 4-Dashboard Assembly | 28 | 154 | 161 | 7 | 2 | 0
5 | Documentation | This phase is dedicated to producing all required project documentation, such as the case study, GitHub repository description, and illustrative SQL queries. | 27 | 6d | 2025-08-01 | 2025-08-06 | BA PM | Lashawn Fofung | 100% | Not Started | 0% | Gray | [5 empty] | 5-Documentation | 29 | 134 | 162 | 5 | 1 | 4
5.1 | Write Case Study | Draft comprehensive project case study outlining analysis, insights, and recommendations. | 28 | 3d | 2025-08-01 | 2025-08-03 | BA PM | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Draft Case Study Document | Case study includes all required sections (Executive Summary, Analysis, Recommendations); Content is clear and is well-supported. |  | 5-Documentation | 30 | 162 | 163 | 1 | 2 | 0
5.2 | Write Tableau Story Summary | Create a brief narrative summary for Tableau Story. | 30 | 1d | 2025-08-04 | 2025-08-04 | BA PM | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Tableau Story Summary Text | Summary is concise, highlights key insights, and is suitable for a Tableau Story narrative. |  | 5-Documentation | 31 | 162 | 164 | 2 | 2 | 0
5.3 | Formulate SQL Queries | Develop illustrative SQL queries for use cases and case studies. | 31 | 2d | 2025-08-05 | 2025-08-06 | BA PM | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | SQL Query Examples Document | Queries logically represent data extraction/analysis for key insights; Syntax is correct. |  | 5-Documentation | 32 | 162 | 165 | 3 | 2 | 0
5.4 | Project Documentation Complete Milestone | All required project documentation (Case Study, Insightful Questions, GitHub Repo Description, SQL Queries, Tableau Story Summary) is drafted, reviewed, and finalized. | 32 | 0 | 2025-08-06 | 2025-08-06 | PM | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Case Study Document, GitHub Repo Description, SQL Queries, Tableau Story Summary | All required documentation components are drafted, accurate, comprehensive, and reviewed; Ready for final submission. | Risks: Time overruns (for comprehensive documentation). | 5-Documentation | 33 | 162 | 166 | 4 | 2 | 0
6 | Review & Closeout | This phase involves internal testing, addressing feedback, and formalizing the project's completion and submission. | 33 | 5d | 2025-08-07 | 2025-08-11 | BA Dev PM QA | Lashawn Fofung | 100% | Not Started | 0% | Gray | [5 empty] | 6-Review & Closeout | 34 | 134 | 167 | 6 | 1 | 6
6.1 | Internal review & testing | Conduct thorough testing of dashboard functionality and data accuracy. | 33 | 1d | 2025-08-07 | 2025-08-07 | BA Dev QA | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Testing Feedback Log (internal) | Dashboard functionality verified; Data accuracy confirmed; Performance reviewed; Performance reviewed. | Risk: Time overruns (for revisions). | 6-Review & Closeout | 35 | 167 | 168 | 1 | 2 | 0
6.2 | Address feedback & revisions | Incorporate feedback from reviews and make necessary adjustments. | 35 | 1d | 2025-08-08 | 2025-08-08 | BA Dev QA | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Revised Tableau Workbook & Docs | All identified feedback and necessary revisions have been incorporated and re-verified. |  | 6-Review & Closeout | 36 | 167 | 169 | 2 | 2 | 0
6.3 | Publish to Tableau Public | Publish the final Tableau workbook to Tableau Public. | 36 | 1d | 2025-08-09 | 2025-08-09 | BA Dev QA | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Published Dashboard URL | Dashboard is successfully published to Tableau Public and accessible via a shareable link. | Risk: Tableau technical challenges (publishing issues) | 6-Review & Closeout | 37 | 167 | 170 | 3 | 2 | 0
6.4 | Finalize Github Repo description and supporting project documents | Update the README content for project's GitHub repository. | 37 | 1d | 2025-08-10 | 2025-08-10 | BA Dev PM | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | README.md file content and for case studies, links to Tableau Public, SQL queries, and data file. | Description is concise, accurate, includes key features and usage instructions, and follows Markdown format. |  | 6-Review & Closeout | 38 | 167 | 171 | 4 | 2 | 0
6.5 | Final project submission | Submit all project deliverables as per requirements. | 38 | 1d | 2025-08-11 | 2025-08-11 | BA Dev PM | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | All Project Deliverable Submitted | All required project files and documents are submitted to the designated platform. | Risk: Time overruns. | 6-Review & Closeout | 39 | 167 | 172 | 5 | 2 | 0
6.6 | Project Closed & Submitted Milestone | Internal review and testing are complete, feedback is addressed, the workbook is published (if applicable), and all project deliverables are formally submitted. | 39 | 0 | 2025-08-11 | 2025-08-11 | PM | Lashawn Fofung | 100% | Not Started | 0% | Gray |  |  | Final Project Submission (e.g., URL to published dashboard, all project files) | Internal review and testing are passed; All feedback has been addressed; All final deliverables are formally submitted. | Risks: Time overruns (for revisions or submission issues); Tableau publishing issues. | 6-Review & Closeout | 40 | 167 | 173 | 6 | 2 | 0